Coddenham Parish Council-churchyard wall repair.

30 April 2025

Josh Halton-Farrow of Wright Consulting (WC)-a conservation engineer-viewed the churchyard wall on 18 February 2025 with Donald Burton and produced a Schedule of Works (SoW).  His charges for this work were c.£2,100 (ex VAT). The SoW is described as worst case and we are advised that the scope of works could be reduced to suit the budget if required.

The document is ready to issue to the relevant authorities for approval and to contractors for pricing.

Josh Halton Farrow recommended that we approach the following contractors for prices. The contractors will not charge to quote for works

- N.D.Willan Building Contractors Ltd

David Willan - David@ndwillanbuilders.co.uk. Cawston Cottage, Heydon Road, Norwich, NR10 4HZ

- Herringbone Restoration Ltd

Steve Ankin - herringbonerestoration1@gmail.com, Herringbone Restoration Ltd, Lakeside Lodge, Fen Road, Pidley, PE28 9BJ

- F.A Valiant & Son Ltd

Tom Austin - Tom.austin@favaliant.co.uk

WC’s proposed charges for assisting the council in issuing the SoW document to at least three contractors and preparing a report discussing the tender returns and giving contractor recommendation, would be £1,320 plus expenses and VAT.

The council is requested to approve instruction of Wright Consulting to undertake this activity and to incur these costs.

In addition, WC’s proposed charges for assisting the council

- In obtaining the required permissions (i.e. LBC application and/or List B application) would be on a time charge basis in accordance with standard hourly rates (as per the attached hourly rates schedule) with a capped fee budget of £1,760 plus expenses and VAT.

- In instructing a contractor and managing the works on site under a JCT Minor Works Contract as Contract Administrator, would be on a time charge basis in accordance with standard hourly rates (as per the attached hourly rates schedule), but with a capped fee budget of £4,400 plus expenses and VAT. This figure allows for chairing one pre-contract meeting with the successful tenderer and four further visits or meetings on site during the construction works to review progress and answer Contractor queries. This fee budget assumes an estimated project cost in the order of up to £100k. Any other time undertaken to provide advice not included within this brief would be charged using standard hourly rates, as attached plus expenses and VAT.

It is proposed that, once the contractors have submitted tenders and the council has received the recommendations of WC, the council considers what further steps are required including revised scope of works, fund raising to meet the costs of any works, obtaining permissions and consents, timetable and scheduling of works and additional professional fees

4 November 2025

1	The tenders from the three prospective contractors and tender analysis from Josh Halton-Farrow of Wright Consulting were circulated in July 2025 by the clerk. A summary was included in the churchyard report presented to the council meeting in September 2025.

2	Cllrs. Mills, Burton and Gregory had a Teams call on 23 September 2025 with Josh Halton-Farrow (JHF) of AC Wright Consulting on the tender analysis. His view was very much that contractor C (the most expensive) was disinclined to do the job and should be eliminated from further consideration.

In relation to contractor A (the least expensive) and contractor B, his view was that both would undertake the work proficiently and, therefore, the decision really came down to price (given the two main criteria for public procurement decisions are quality/price). JHF has worked with both contractor A and B on churchyard walls recently. Photos have been supplied and circulated to councillors by the clerk

He did say that he thought contractor A would be easier to manage on site and was keener for the work (as one director of the firm lives relatively close by).

JHF agreed with Cllrs. Mills and Gregory that contractor B had produced the most professional tender but was of the view that was because they were a bigger firm and had greater resource (and, no doubt, overhead- reflected in price) and that this did not mean any higher proficiency for works such as these.

We noted that the main difference between the two contractor was in the length of time they estimated to undertake the works (7 weeks as against 10). Given the impact that this might have on the road, we asked JHF to revert to the contractors to ascertain further details of proposed works schedules and traffic management plans.

3 	JHF of Wright Consulting subsequently reported on 20/10/2025 that he had made the following requests of contractors A and B:

    - How many weeks of the programme do you expect to need traffic management in place?

    - Could the roadside and churchyard side works be phased to reduce the time the traffic management is in place?

    - What traffic management would you recommend? Is it a road closure or single lane with traffic lights? Do you have a rough cost?

    - Is there any way to reduce the time the traffic management needs to be in place?

    - They will likely want to increase the contract's liquidated damages of £100/week to £1000/week for the traffic management programme. Will your quote need to increase to compensate for this?

Contractor A responses

- 5 weeks (of 10)

- 5 weeks internal / 5 weeks external

- Single lane traffic lights

- No

- We would add an additional £5,000 to cover damages.

Contractor B responses

"We have approached a traffic management company to seek advice including an approximate cost, and they have asked when the project is likely to commence?

The traffic management will need to be in place for the full duration of the work, and it may be prudent to have an additional week in place for surveying/snagging, etc. We have assumed access to both sides of the wall to complete the work in the timeframe.

We believe that a single lane closure with traffic lights would be suitable and are awaiting feedback on this. It is an awkward length of road when considering the approach to the site from both directions, with narrow lanes, reduced sight lines, junctions, etc.

It might be possible to reduce the programme by employing additional labour to complete the work, however this will also increase costs, and the reduction in programme is likely to be marginal.

We cannot accept any increase in the liquidated damages for a project of this type and scale."

4	On 14/10/25, Cllrs Denning and Gregory met Ian Galbraith of the parochial parish council (PCC) and updated him on the progress of the project thus far. We informed him that the expectation was that the council would make a formal approach to the PCC to start the approvals process in January 2026. Mr Galbraith mentioned that, approx. eight years ago, the council had been prepared to undertake some significant repair works to the wall but the diocesan architect had been of the view that this was not required and, as a result, only very minor repair works had been undertaken. Mr Galbraith also informed the council that the PCC are looking at the repairs required to the concrete drainage channel around the church base (which is believed to be causing damp) and the rain soakaway which is located close to the church doorway.

Decisions required

- Appointment of a contractor for the works (subject to contract, required approvals and funding).

- Instruction of Josh Halton-Farrow of Wright Consulting to prepare an advice to be presented at the PCC meeting in January 2026, to progress the required approvals and to engage with the diocesan architect.

- Actions to be undertaken as regards possible funding of the works.

28 December 2025

Following on from the decisions at the last meeting in November 2025, Wright Consulting (WC) have been instructed to prepare an advice to be presented at the PCC meeting in January 2026, assist the council in obtaining the required permissions (i.e. LBC application and/or List B application) and to engage with the diocesan architect. Costs incurred to date and to be incurred are covered in the financial reports.

Herringbone have been informed that they are the successful tenderer (subject to contract, required approvals and funding) but there has not yet been formal instruction of WC or Herringbone in relation to contracting pending responses from the PCC/diocesan architect.

A meeting is to be scheduled of the funding sub-group.

Update May 2026

The funding sub-group met on 22 April 2026. It has not been possible to identify any grants available for application and it is considered that the project is unlikely to attract significant donations, crowd funding or similar. Accordingly, it is proposed that the required funds are borrowed from the PWLB or possibly other local organisations, subject to terms. Cllr Mills is exploring this possibility. It is noted that local councils in the UK require formal borrowing approval (sanction) from the Ministry of Housing, Communities and Local Government (MHCLG) if they intend to borrow money for terms exceeding 12 months.

Following the Parish Council meeting on 18 March 2026,  the clerk has intructed Wright Consulting (WC) to commence the services contemplated in section 4 of the quote and now prepare a form of JCT Minor Works Contract for the works for approval by the council. WC were instructed that (1) the council is concerned to have sight of the proposed traffic management plan and timeline for the works before it approves the form of contract and (2) the council does not believe that the winter would be a good time to undertake works so we are possibly looking at Spring 2027.

List B approval  was granted on 21 April 2026 and WC had advised that they do not believe any further  consents are required for the works.

The question of adding pozzolan to the lime mortar remains a point of discussion.

WC have advised that a traffic management plan will be produced nearer to the start date in conjunction with the traffic management company.

WC have produced a draft form of contract  based on a JCT minor works contract which is in the pack for the meeting.  This proposes that works start in march 2027 and end in may 2027.

Decision required

It is proposed that amendments to the contract are made to ensure that the council  has the right to approve the  form of traffic management plan proposed and the traffic management company as a pre-condition to commitment.

Cllr Sarah Gregory

24/5/2026

Invoices from Wright Consulting

| Date | Number | Amount | VAT | Total | Stage |
| --- | --- | --- | --- | --- | --- |
| 20/3/25 | 2025-073 | 2107.74 | 421.55 | 2529.29 | Stage 1 |
| 3/9/25 | 2025-219 | 1027.62 | 205.52 | 1233.14 | Stage 2 |