				Sizewell C Construction Update June 2026












				Introduction 



	Works to improve and install infrastructure to facilitate the construction of Sizewell C progresses well. We are aiming to reduce disruption as much as possible as the works continue and thank the East Suffolk community for their patience. 
The roundabouts on the A12 are nearing completion and the Park and Rides are increasing in capacity. The construction of the Marine Bulk Import Facility (MBIF) to enable materials to be delivered by sea is well underway and will be across the beach by July. Our rail teams are working hard to enable trains to start accessing the temporary construction area, therefore meeting our commitment to bring 60 per cent of materials in by sea and train.



	Off Site Infrastructure



	Friday Street and Yoxford Roundabout:
The completion of the construction phase to Yoxford and Friday Street roundabouts is on schedule for the end of July. Traffic cones and compounds will be removed at Yoxford and the roundabout will be handed over to Suffolk County Council Highways.  At Friday Street, traffic management will be significantly reduced, however access to the construction of the two-village bypass for Stratford St Andrews and Farnham will continue.  Grass seeding will be sown, ahead of further planting in the Autumn. 
Two Village Bypass and Sizewell Link Road
Both the Two Village Bypass and the Sizewell Link Road are now in full construction.
Specifically, works are underway to build the bridges needed to pass over the River Alde on the two village bypass and the East Suffolk railway line on the link road.
To enable the construction of the Sizewell Link Road, road closures are required to facilitate the construction of the road.  These include:
Moat Road and George Road, where a new road layout is being constructed. This work is expected to be completed by 7 August 2026. However, Moat Road will remain closed from the B1122.
Littlemore Road remains permanently closed. We will shortly be removing diversion signs from the area to declutter signage.
Abbey Lane re-opening has had slight delay by a week to complete the required improvements works of the road. The reopening will now be from the 6 July.
Pretty Road will also close from 6 July to allow construction of a bridge over the link road.
Fordley Road is also subject to a required closure, we will update in due course on the timings of this.
B1122 We are progressing the new access requirement to the construction site north of Middleton Moor, which we expect to be finished early July.  This will require two-way traffic light management on 29 and 30 June in order to complete the works.
A12 Road improvements
Work in Marlesford to improve footways, construct a signalised road crossing, widen road junctions and improve road signage are ongoing. Works will then progress to Little Glemham to construct similar road safety measures and road infrastructure improvements and upgrades.
In and around Leiston
Road improvement works continue around Abbey Road, Lovers Lane and Eastbridge Road. Over the coming month road resurfacing around the rail line will continue.
Work is also continuing along the Bridleway 19 diversion and the plaza roundabout, which will become the main access point to the Sizewell C construction sites once complete. This is expected to be operational in early 2027.
We have completed the first phase of the B1122 road improvements, resurfacing works at Middleton Moor will be carried out in September.  
Park and Rides
We continue to gradually increase capacity at both the Northern and Southern Park and Rides as the construction works of both sites continue at pace.  We are looking forward to re-opening Willow Marsh Lane in July.  Our contractors will move on to A12 road improvements from the station to the Jet garage including resurfacing, a new pedestrian crossing and road markings. This will require night time road closures Monday 20 July – Wednesday 22 July.












				Rail



	Good progress has been made along the railway corridor. Track has now been laid along the Green Rail Route, track and level crossing has been installed at Abbey Road and Buckleswood Road has also been completed.
Over the coming months, level crossing gates will be installed or upgraded along the Saxmundham to Leiston railway line. Road closures will be required to allow these upgrades to take place.
Important utilities work on the Leiston Level Crossing on Station Road are required to be made in August, specifically upgrades for domestic gas piping.  We are working closely with Cadent Gas who will be carrying out these works throughout August and will require a full road closure.  Pedestrian crossing will be maintained throughout the works.
Please look out for notices of these closures on the works tracker.



	Main Construction Area (MCA) and Temporary Construction Area (TCA) 



	Works on the Marine Bulk Import Facility are progressing from the main development site towards the sea, and we expect to enter the sea in July. As a result, the marshalling system along the beach footpath will be removed. Works will then continue to complete the facility by the end of the year.  Sheet piling for the temporary sea defence is also scheduled to be completed by July. 
Once this is complete, works will begin in the autumn to install rock armour around the southern end of the temporary sea defence. This work is required to protect Sizewell B operations. To prepare for the installation, rock deliveries will begin in July. The rocks will be transported by road from the Port of Great Yarmouth to the site using our designated route. Further preparation works will also take place on the beach ahead of installation.
Some alterations will be made to the beach footpath to accommodate construction of the rock armour and help ensure the footpath remains open while the works are carried out.












				Upcoming Events and Community Forums



	Over the summer we are hosting and supporting a number of events including a three-day archaeology event, Cinema in the park and a open day at Wild Aldhurst. Further information can be found at www.sizewellc.com/community
The Main Development Community Forum will be held on Wednesday 8 July at the Leiston Town Athletic Association Victory Rd, Leiston IP16 4DQ. Arrival from 1745pm starting promptly at 1800pm. Further forum information can be found here: Forums & Local Information - Sizewell C
We appreciate your continued patience while these works are carried out. We will continue to provide updates as work progresses and will share information about road closures, traffic management and other activities through our usual channels, including the works tracker here: www.szcworkstracker.co.uk.  Please do sign up for our email and SMS notifications.
Alternatively, if you have any questions, please do visit us at the information office, 48 – 50 High Street, Leiston IP16 4EW  09:30 -17:00 weekdays (closed for lunch 12:30 -13:30) or call 0800 197 6102 or email: info@sizewellc.com
 
 












